## SPRINT BACKLOG
SPRINT 1 BACKLOG |  |  |  | Section 3, Group 6, ThinkFeelImagine: 6788112 Waris (Beam), 6788124 Leenawat (Sunny), 6788082 Tanyawat (Wave), 6788217 Natchapol (Boss), 6788031 Nattanan (Nut)
ID | User Story | Tasks | #Hours | Owner | Status | Estimated effort hours (relative to team capacity) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
A-01 | As Amara, I want to view each village’s latest technician check-in and reading-submission status so I can identify villages needing follow-up. | Build village-status API using latest check-ins and submitted readings. | 4 | Wave | Completed | 18 | - | - | - | - | 3 | - | - | 1 | - | - | - | - | - | - | -
|  | Build the village dashboard with check-in and reading status. | 6 | Sunny | Completed |  | - | - | - | 2 | - | - | 4 | - | - | - | - | - | - | - | -
|  | Flag villages with no check-in or reading update for more than 24 hours. | 3 | Boss | Completed |  | - | - | - | - | - | - | - | - | 3 | - | - | - | - | - | -
|  | Test current status and the 24-hour stale-update boundary. | 2 | Nut | Completed |  | - | - | - | - | - | - | - | - | - | - | - | - | 2 | - | -
|  | Integrate live data and fix dashboard acceptance-test defects. | 3 | Wave | Completed |  | - | - | - | - | - | - | - | - | - | - | 3 | - | - | - | -
A-02 | As a technician, I want to record my village check-in with time, location and notes so Amara can track visits. | Define shared village/meter data and save authenticated technician check-ins. | 4 | Wave | Completed | 17 | 4 | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  | Build the check-in form for village, time, location and notes. | 4 | Sunny | Completed |  | - | 4 | - | - | - | - | - | - | - | - | - | - | - | - | -
|  | Persist offline or invalid-location check-ins locally as pending sync. | 4 | Beam | Completed |  | - | - | 4 | - | - | - | - | - | - | - | - | - | - | - | -
|  | Integrate check-in visibility for Amara and pending-location handling. | 3 | Boss | Completed |  | - | - | - | - | - | 3 | - | - | - | - | - | - | - | - | -
|  | Test online save, offline persistence and invalid-location pending status. | 2 | Nut | Completed |  | - | - | - | - | - | - | - | - | - | - | - | - | 2 | - | -
A-03 | As Amara, I want technicians’ submitted readings to be validated and stored so the dashboard shows reliable reading status. | Create the shared reading API and storage for meter/village, value, unit and date. | 4 | Wave | Completed | 18 | 1 | - | 3 | - | - | - | - | - | - | - | - | - | - | - | -
|  | Validate reading values and reject invalid or non-numeric submissions. | 4 | Beam | Completed |  | - | - | 2 | - | 2 | - | - | - | - | - | - | - | - | - | -
|  | Connect reading submission and validation messages to dashboard status. | 4 | Sunny | Completed |  | - | - | - | - | - | - | 2 | - | 2 | - | - | - | - | - | -
|  | Integrate queued readings with the shared sync service and dashboard. | 4 | Boss | Completed |  | - | - | - | - | - | - | - | - | - | - | 4 | - | - | - | -
|  | Test valid and invalid readings plus offline submission and later sync. | 2 | Nut | Completed | bar: Day 1 to Day 15
T-10 | As a technician, I want to enter meter readings and see previous values and anomaly warnings so I can capture accurate readings offline or online. | Build meter selection and value/unit/date entry using the shared reading API. | 6 | Sunny | Completed | 18 | - | 2 | - | 4 | - | - | - | - | - | - | - | - | - | - | -
|  | Retrieve and display the previous reading for the selected meter. | 4 | Wave | Completed |  | - | - | 2 | - | 2 | - | - | - | - | - | - | - | - | - | -
|  | Implement anomaly warnings and preserve the entered reading for review. | 4 | Beam | Completed |  | - | - | - | - | 4 | - | - | - | - | - | - | - | - | - | -
|  | Connect meter entry to offline queueing and verify previous-value/anomaly paths. | 4 | Boss | Completed |  | - | - | - | - | - | 2 | - | - | 2 | - | - | - | - | - | -
T-12 | As a technician, I want queued data to sync when connectivity returns so check-ins and readings reach Amara without being lost. | Build shared persistent queue and reconnect-triggered sync for both record types. | 6 | Beam | Completed | 24 | 6 | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  | Handle conflicts and failed sync with retained queue items and safe retries. | 6 | Beam | Completed |  | - | - | - | - | - | - | - | 6 | - | - | - | - | - | - | -
|  | Show pending/synced/error states and add manual retry controls. | 4 | Boss | Completed |  | - | - | - | - | - | - | - | - | - | - | 1 | 3 | - | - | -
|  | Integrate end-to-end sync and ensure retries do not create duplicate records. | 4 | Wave | Completed |  | - | - | - | - | - | - | - | 4 | - | - | - | - | - | - | -
|  | Test reconnect, conflict, failed retry and recovery across all five stories. | 4 | Nut | Completed |  | - | - | - | - | - | - | - | - | - | - | - | - | - | 4 | -
|  | TOTAL PLANNED HOURS | 95 |  |  | 95 | 11 | 6 | 11 | 6 | 11 | 5 | 6 | 11 | 7 | - | 8 | 3 | 5 | 5 | -

## PROJECT DETAILS
PROJECT NUMBER | 6
PROJECT NAME | ThinkFeelImagine
PROJECT MANAGER | 6788082 Tanyawat (Wave)
DATE | 2026-09-17 22:06
VERSION | 1

## RESOURCES
Useful resources
Burndown Chart Template
Daily Scrum Meeting Template
Deployment Plan Template
Product Backlog Template
Project Management Templates